# Core mutual action plan

Use it when you want one clean plan to adapt to any B2B deal of 30 to 90 days.

| Deal |  |
| --- | --- |
| Target signature date | 2027-01-29 |
| Seller |  |
| Buyer |  |
| Seller owner |  |
| Buyer owner |  |

## How to use

1. Every due date counts from the target signature date above. The Excel version re-dates the whole plan from one cell.

2. Mark each row Not started, In progress or Completed as the deal moves.

3. Put a name next to every role, so each row has one owner on each side.

4. Send the plan to your buyer before the planning call and ask them to correct the approvers and lead times.

5. Update the status on every call and note the evidence when a row is completed.

Start a live plan in demoshake

Source: demoshake.com/guides/mutual-action-plan-template

## Plan

| Milestone | Action Item | Seller owner | Buyer owner | Due date | Days before signature | Status | Dependency | Evidence of completion | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Agree on the problem and the date | Hold a mutual planning call and agree on a target signature date | Account Executive | Champion | 2026-11-30 | 60 | Not started |  | Target signature date written at the top of this plan |  |
| Agree on the problem and the date | Write down the three outcomes this purchase must deliver | Account Executive | Champion | 2026-12-04 | 56 | Not started | Hold a mutual planning call and agree on a target signature date | Success criteria agreed by the Champion in writing |  |
| Agree on the problem and the date | List everyone who must approve the purchase, with their role | Account Executive | Champion | 2026-12-06 | 54 | Not started |  | Buying group list with names, roles and sign-off order |  |
| Evaluate the solution | Run a demo built around the agreed success criteria | Sales Engineer | Technical Evaluator | 2026-12-15 | 45 | Not started | Write down the three outcomes this purchase must deliver | Demo recording and follow-up questions shared |  |
| Evaluate the solution | Test the product against each success criterion | Sales Engineer | Technical Evaluator | 2026-12-25 | 35 | Not started | Run a demo built around the agreed success criteria | Scorecard with a pass or fail per criterion |  |
| Evaluate the solution | Share the evaluation results with the buying group | Account Executive | Champion | 2026-12-30 | 30 | Not started | Test the product against each success criterion | Evaluation summary sent to every approver |  |
| Build the business case | Draft the business case with cost, savings and payback period | Account Executive | Champion | 2027-01-01 | 28 | Not started | Share the evaluation results with the buying group | Business case document reviewed by the Champion |  |
| Build the business case | Confirm budget is approved for this purchase | Account Executive | Economic Buyer | 2027-01-05 | 24 | Not started |  | Budget line or approval email from the Economic Buyer |  |
| Build the business case | Present the business case to the Economic Buyer | Account Executive | Champion | 2027-01-08 | 21 | Not started | Draft the business case with cost, savings and payback period | Economic Buyer agrees to move to contract |  |
| Pass the security review | Send the security questionnaire to the seller | Seller Security | Security | 2026-12-28 | 32 | Not started |  | Questionnaire received by the seller |  |
| Pass the security review | Return the completed questionnaire with the SOC 2 report | Seller Security | Security | 2027-01-04 | 25 | Not started | Send the security questionnaire to the seller | Completed questionnaire and report delivered |  |
| Pass the security review | Approve the security review or list the open findings | Seller Security | Security | 2027-01-11 | 18 | Not started | Return the completed questionnaire with the SOC 2 report | Written security approval |  |
| Agree the contract | Register the seller as a vendor | Deal Desk | Procurement | 2027-01-08 | 21 | Not started |  | Vendor ID issued |  |
| Agree the contract | Send the order form and master agreement | Deal Desk | Procurement | 2027-01-09 | 20 | Not started |  | Contract package received by Procurement |  |
| Agree the contract | Return contract redlines | Seller Legal | Legal | 2027-01-15 | 14 | Not started | Send the order form and master agreement | Redlined agreement sent back |  |
| Agree the contract | Agree final terms and pricing | Account Executive | Procurement | 2027-01-22 | 7 | Not started | Return contract redlines | Clean agreement with no open redlines |  |
| Sign and kick off | Route the contract for signature | Deal Desk | Procurement | 2027-01-26 | 3 | Not started | Agree final terms and pricing | Signature request sent to the signer |  |
| Sign and kick off | Sign the contract | Account Executive | Economic Buyer | 2027-01-29 | 0 | Not started | Route the contract for signature | Countersigned contract |  |
| Sign and kick off | Book the kickoff call with the implementation team | Implementation Lead | Champion | 2027-01-29 | 0 | Not started |  | Kickoff invite accepted |  |