## Cover
Core mutual action plan
Use it when you want one clean plan to adapt to any B2B deal of 30 to 90 days.
Deal
Target signature date | 2027-01-29
Seller
Buyer
Seller owner
Buyer owner
How to use
1. Enter your target signature date above. Every due date on the Plan sheet is counted from it.
2. Change a row's days before signature to move that row alone.
3. Put a name next to every role, so each row has one owner on each side.
4. Send the plan to your buyer before the planning call and ask them to correct the approvers and lead times.
5. Update the status on every call and note the evidence when a row is completed.
Start a live plan in demoshake
Source: demoshake.com/guides/mutual-action-plan-template

## Plan
Milestone | Action Item | Seller owner | Buyer owner | Due date | Days before signature | Status | Dependency | Evidence of completion | Notes
Agree on the problem and the date | Hold a mutual planning call and agree on a target signature date | Account Executive | Champion | 2026-11-30 | 60 | Not started |  | Target signature date written at the top of this plan
Agree on the problem and the date | Write down the three outcomes this purchase must deliver | Account Executive | Champion | 2026-12-04 | 56 | Not started | Hold a mutual planning call and agree on a target signature date | Success criteria agreed by the Champion in writing
Agree on the problem and the date | List everyone who must approve the purchase, with their role | Account Executive | Champion | 2026-12-06 | 54 | Not started |  | Buying group list with names, roles and sign-off order
Evaluate the solution | Run a demo built around the agreed success criteria | Sales Engineer | Technical Evaluator | 2026-12-15 | 45 | Not started | Write down the three outcomes this purchase must deliver | Demo recording and follow-up questions shared
Evaluate the solution | Test the product against each success criterion | Sales Engineer | Technical Evaluator | 2026-12-25 | 35 | Not started | Run a demo built around the agreed success criteria | Scorecard with a pass or fail per criterion
Evaluate the solution | Share the evaluation results with the buying group | Account Executive | Champion | 2026-12-30 | 30 | Not started | Test the product against each success criterion | Evaluation summary sent to every approver
Build the business case | Draft the business case with cost, savings and payback period | Account Executive | Champion | 2027-01-01 | 28 | Not started | Share the evaluation results with the buying group | Business case document reviewed by the Champion
Build the business case | Confirm budget is approved for this purchase | Account Executive | Economic Buyer | 2027-01-05 | 24 | Not started |  | Budget line or approval email from the Economic Buyer
Build the business case | Present the business case to the Economic Buyer | Account Executive | Champion | 2027-01-08 | 21 | Not started | Draft the business case with cost, savings and payback period | Economic Buyer agrees to move to contract
Pass the security review | Send the security questionnaire to the seller | Seller Security | Security | 2026-12-28 | 32 | Not started |  | Questionnaire received by the seller
Pass the security review | Return the completed questionnaire with the SOC 2 report | Seller Security | Security | 2027-01-04 | 25 | Not started | Send the security questionnaire to the seller | Completed questionnaire and report delivered
Pass the security review | Approve the security review or list the open findings | Seller Security | Security | 2027-01-11 | 18 | Not started | Return the completed questionnaire with the SOC 2 report | Written security approval
Agree the contract | Register the seller as a vendor | Deal Desk | Procurement | 2027-01-08 | 21 | Not started |  | Vendor ID issued
Agree the contract | Send the order form and master agreement | Deal Desk | Procurement | 2027-01-09 | 20 | Not started |  | Contract package received by Procurement
Agree the contract | Return contract redlines | Seller Legal | Legal | 2027-01-15 | 14 | Not started | Send the order form and master agreement | Redlined agreement sent back
Agree the contract | Agree final terms and pricing | Account Executive | Procurement | 2027-01-22 | 7 | Not started | Return contract redlines | Clean agreement with no open redlines
Sign and kick off | Route the contract for signature | Deal Desk | Procurement | 2027-01-26 | 3 | Not started | Agree final terms and pricing | Signature request sent to the signer
Sign and kick off | Sign the contract | Account Executive | Economic Buyer | 2027-01-29 | 0 | Not started | Route the contract for signature | Countersigned contract
Sign and kick off | Book the kickoff call with the implementation team | Implementation Lead | Champion | 2027-01-29 | 0 | Not started |  | Kickoff invite accepted
Formulas:
Due date = Cover!$B5-[Days before signature]