## Cover
Enterprise mutual action plan
Use it when five or more people on the buying side must approve, and security, procurement and legal each run their own review.
Deal
Target signature date | 2027-01-29
Seller
Buyer
Seller owner
Buyer owner
How to use
1. Enter your target signature date above. Every due date on the Plan sheet is counted from it.
2. Change a row's days before signature to move that row alone.
3. Put a name next to every role, so each row has one owner on each side.
4. Send the plan to your buyer before the planning call and ask them to correct the approvers and lead times.
5. Update the status on every call and note the evidence when a row is completed.
Start a live plan in demoshake
Source: demoshake.com/guides/mutual-action-plan-template

## Plan
Milestone | Action Item | Seller owner | Buyer owner | Due date | Days before signature | Status | Dependency | Evidence of completion | Notes
Discovery and mutual commitment | Write a one-page problem statement in the buyer's own words | Account Executive | Champion | 2026-10-01 | 120 | Not started |  | Problem statement approved by the Champion
Discovery and mutual commitment | Agree a target signature date tied to a business event | Account Executive | Champion | 2026-10-06 | 115 | Not started | Write a one-page problem statement in the buyer's own words | Date and the event behind it written into this plan | A date with no event behind it slips. Tie it to a board meeting, a contract expiry or a launch.
Discovery and mutual commitment | Map every approver, their concern and the order they sign off in | Account Executive | Champion | 2026-10-11 | 110 | Not started |  | Buying group map with names, roles and sign-off order
Discovery and mutual commitment | Walk through the buyer's purchasing process step by step | Account Executive | Procurement | 2026-10-16 | 105 | Not started | Map every approver, their concern and the order they sign off in | Every review and approval in the process has a row in this plan | Ask what happened on the last software purchase of this size. That answer is the real process.
Success criteria | Draft measurable success criteria with a baseline for each | Sales Engineer | Technical Evaluator | 2026-10-21 | 100 | Not started | Write a one-page problem statement in the buyer's own words | Criteria document with current baseline numbers
Success criteria | Sign off the success criteria as the bar for the evaluation | Account Executive | Executive Sponsor | 2026-10-26 | 95 | Not started | Draft measurable success criteria with a baseline for each | Written approval from the Executive Sponsor
Technical evaluation | Run a demo for each team that will use the product | Sales Engineer | End Users | 2026-10-31 | 90 | Not started | Sign off the success criteria as the bar for the evaluation | Demo recordings shared with each team
Technical evaluation | Agree the pilot scope, data, users and exit criteria | Sales Engineer | Technical Evaluator | 2026-11-05 | 85 | Not started | Run a demo for each team that will use the product | Pilot plan signed off by the Technical Evaluator
Technical evaluation | Run the pilot and score it against the success criteria | Sales Engineer | Technical Evaluator | 2026-11-25 | 65 | Not started | Agree the pilot scope, data, users and exit criteria | Pilot scorecard with a result per criterion
Technical evaluation | Present the pilot results to the buying group | Account Executive | Champion | 2026-11-30 | 60 | Not started | Run the pilot and score it against the success criteria | Readout sent to every approver on the buying group map
Business case | Build the business case from the pilot results | Account Executive | Champion | 2026-12-05 | 55 | Not started | Present the pilot results to the buying group | Business case with cost, savings and payback period
Business case | Check the savings model with Finance | Account Executive | Finance | 2026-12-10 | 50 | Not started | Build the business case from the pilot results | Finance agrees with the assumptions in writing
Business case | Confirm which budget line pays for this and that it is released | Account Executive | Economic Buyer | 2026-12-15 | 45 | Not started |  | Budget owner and amount confirmed
Executive alignment | Hold an executive meeting between both sponsors | Sales Leader | Executive Sponsor | 2026-12-18 | 42 | Not started | Check the savings model with Finance | Meeting held and next steps confirmed by email
Executive alignment | Record the decision to proceed to contract | Account Executive | Economic Buyer | 2026-12-22 | 38 | Not started | Hold an executive meeting between both sponsors | Go decision in writing from the Economic Buyer
Security and IT review | Submit the seller to vendor risk intake | Seller Security | Security | 2026-11-20 | 70 | Not started |  | Intake ticket opened with a risk tier | Start security as soon as the pilot is scoped. It is the review most likely to move the date.
Security and IT review | Send the SOC 2 report, pen test summary and completed questionnaire | Seller Security | Security | 2026-11-30 | 60 | Not started | Submit the seller to vendor risk intake | Security package delivered
Security and IT review | Approve the integration design, SSO and data flows | Sales Engineer | IT | 2026-12-15 | 45 | Not started |  | Architecture review sign-off
Security and IT review | Close the findings and sign off the security review | Seller Security | Security | 2026-12-25 | 35 | Not started | Send the SOC 2 report, pen test summary and completed questionnaire | Signed vendor risk approval
Procurement | Register the seller as a vendor | Deal Desk | Procurement | 2026-12-20 | 40 | Not started |  | Vendor ID issued
Procurement | Send the commercial proposal and order form | Account Executive | Procurement | 2026-12-24 | 36 | Not started | Record the decision to proceed to contract | Proposal received by Procurement
Procurement | Agree pricing, term and payment schedule | Account Executive | Procurement | 2027-01-09 | 20 | Not started | Send the commercial proposal and order form | Final order form with no open comments
Legal review | Send the master agreement and data processing addendum | Seller Legal | Legal | 2026-12-24 | 36 | Not started | Record the decision to proceed to contract | Agreement received by Legal | Send paper early. Legal queues are first in, first out, and redlines rarely take less than two weeks.
Legal review | Return redlines on the master agreement | Seller Legal | Legal | 2027-01-04 | 25 | Not started | Send the master agreement and data processing addendum | Redlined agreement received
Legal review | Agree the final contract language | Seller Legal | Legal | 2027-01-17 | 12 | Not started | Return redlines on the master agreement | Clean agreement approved by both legal teams
Signature and kickoff readiness | Route the contract to the authorized signer | Deal Desk | Procurement | 2027-01-24 | 5 | Not started | Agree the final contract language | Signature request in the signer's queue
Signature and kickoff readiness | Name the buyer's project lead and admins for implementation | Implementation Lead | Champion | 2027-01-24 | 5 | Not started |  | Project team listed
Signature and kickoff readiness | Sign the contract | Sales Leader | Economic Buyer | 2027-01-29 | 0 | Not started | Route the contract to the authorized signer | Countersigned contract
Signature and kickoff readiness | Book the kickoff within ten working days of signature | Implementation Lead | Champion | 2027-01-29 | 0 | Not started | Name the buyer's project lead and admins for implementation | Kickoff invite accepted
Formulas:
Due date = Cover!$B5-[Days before signature]