# Filled example: Fieldline and Halvorsen Freight

Use it when you want to see what a finished plan looks like before you write your own, with every row owned, dated and evidenced.

| Deal | Halvorsen Freight: Fieldline forecasting rollout |
| --- | --- |
| Target signature date | 2026-12-11 |
| Seller | Fieldline |
| Buyer | Halvorsen Freight |
| Seller owner | Account Executive: Maya Lindqvist |
| Buyer owner | Champion: Daniel Okafor |

## How to use

1. Every due date counts from the target signature date above. The Excel version re-dates the whole plan from one cell.

2. Mark each row Not started, In progress or Completed as the deal moves.

3. Put a name next to every role, so each row has one owner on each side.

4. Send the plan to your buyer before the planning call and ask them to correct the approvers and lead times.

5. Update the status on every call and note the evidence when a row is completed.

Start a live plan in demoshake

Source: demoshake.com/guides/mutual-action-plan-template

## Plan

| Milestone | Action Item | Seller owner | Buyer owner | Due date | Days before signature | Status | Dependency | Evidence of completion | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Agree on the problem and the date | Hold a mutual planning call and agree on 11 December as the signature date | Account Executive: Maya Lindqvist | Champion: Daniel Okafor | 2026-10-02 | 70 | Completed |  | Plan shared in the Deal Room on 2 October | Date works backwards from the Q1 board meeting on 28 January, when Rebecca wants to show the new forecast. |
| Agree on the problem and the date | Write down the three outcomes the rollout must deliver | Account Executive: Maya Lindqvist | Champion: Daniel Okafor | 2026-10-06 | 66 | Completed | Hold a mutual planning call and agree on 11 December as the signature date | Success criteria page approved by Daniel | 1. Forecast accuracy within 5% at the regional level. 2. Weekly forecast call cut from 3 hours to 1. 3. One number for the board, no spreadsheet merges. |
| Agree on the problem and the date | Map every approver and the order they sign off in | Account Executive: Maya Lindqvist | Champion: Daniel Okafor | 2026-10-09 | 63 | Completed |  | Buying group of nine people listed in the Deal Room | Daniel flagged that Nadia's team only takes new vendors into review on Mondays. Built that into the security dates. |
| Prove it on Halvorsen data | Run a demo on last quarter's pipeline from the Nordics region | Sales Engineer: Tomás Reyes | Technical Evaluator: Aisha Rahman | 2026-10-14 | 58 | Completed | Write down the three outcomes the rollout must deliver | Recording and data mapping notes shared in the Deal Room | Aisha asked how we handle split opportunities across regions. Answered in the follow-up with a worked example. |
| Prove it on Halvorsen data | Connect a read-only Salesforce sandbox for the pilot | Sales Engineer: Tomás Reyes | IT: Chris Donnelly | 2026-10-20 | 52 | Completed | Run a demo on last quarter's pipeline from the Nordics region | Sandbox connected, 18 months of history synced | Took four days longer than planned while Chris waited on a connected app approval. |
| Prove it on Halvorsen data | Run a two-week pilot with four regional sales managers | Sales Engineer: Tomás Reyes | End Users: Ella Grant | 2026-10-27 | 45 | Completed | Connect a read-only Salesforce sandbox for the pilot | Pilot scorecard from Ella's group: 4 of 4 managers would switch | Accuracy came in at 4.1% against actuals for the pilot regions. Ella wants mobile access before the full rollout. |
| Prove it on Halvorsen data | Share the pilot results with the buying group | Account Executive: Maya Lindqvist | Champion: Daniel Okafor | 2026-11-02 | 39 | Completed | Run a two-week pilot with four regional sales managers | Pilot readout deck sent to all nine approvers | Marcus replied the same day asking to see the board view. Good signal. |
| Build the business case | Draft the business case from the pilot numbers | Account Executive: Maya Lindqvist | Champion: Daniel Okafor | 2026-11-03 | 38 | Completed | Share the pilot results with the buying group | Business case v2 approved by Daniel | Payback in 7 months, mostly from 26 manager hours a week back from the forecast call. Kept the savings conservative on purpose. |
| Build the business case | Confirm the forecasting budget is released for this fiscal year | Account Executive: Maya Lindqvist | Economic Buyer: Rebecca Shaw | 2026-11-06 | 35 | Completed |  | Email from Rebecca confirming $190,000 is released | Budget sits in the finance transformation line, not sales ops. Rebecca owns it directly. |
| Build the business case | Present the business case to the CFO and the Chief Commercial Officer | Sales Leader: Grace Whitfield | Executive Sponsor: Marcus Bell | 2026-11-11 | 30 | Completed | Draft the business case from the pilot numbers | Go decision recorded in the steering meeting minutes | Grace joined to answer the multi-year pricing question. Rebecca asked for a price hold through January, which we gave. |
| Pass the security review | Submit Fieldline to the vendor risk intake | Seller Security: Ravi Menon | Security: Nadia Petrova | 2026-10-30 | 42 | Completed |  | Intake ticket opened and classified as medium risk | Medium risk because the platform reads opportunity amounts. No personal data beyond rep names. |
| Pass the security review | Return the security questionnaire with the SOC 2 Type II report | Seller Security: Ravi Menon | Security: Nadia Petrova | 2026-11-09 | 32 | Completed | Submit Fieldline to the vendor risk intake | Questionnaire (212 answers) and report uploaded to the Deal Room | Answered in six working days. Shared the pen test summary under NDA at the same time to save a round trip. |
| Pass the security review | Close the open findings on SSO enforcement and data retention | Seller Security: Ravi Menon | Security: Nadia Petrova | 2026-11-17 | 24 | In progress | Return the security questionnaire with the SOC 2 Type II report | Findings log shows both items resolved | SSO is closed. Retention is waiting on Nadia to confirm the 90-day deletion window meets their policy. |
| Pass the security review | Sign off the security review | Seller Security: Ravi Menon | Security: Nadia Petrova | 2026-11-20 | 21 | Not started | Close the open findings on SSO enforcement and data retention | Signed vendor risk approval | Risk: Nadia is out 23 to 27 November, so approval has to land by Friday 20 November or signature slips a week. |
| Confirm the integration plan | Review the integration diagram for Salesforce and the data warehouse | Sales Engineer: Tomás Reyes | IT: Chris Donnelly | 2026-11-13 | 28 | In progress |  | Diagram approved in the architecture review | Chris wants the warehouse sync to run nightly, not hourly, to stay inside their Snowflake credit budget. |
| Confirm the integration plan | Confirm SSO through Okta and the user provisioning method | Sales Engineer: Tomás Reyes | IT: Chris Donnelly | 2026-11-19 | 22 | Not started | Review the integration diagram for Salesforce and the data warehouse | Okta app request approved | SCIM provisioning agreed in principle. Needs a ticket in their IT queue, five-day lead time. |
| Agree the contract | Register Fieldline as a vendor in Coupa | Deal Desk: Owen Park | Procurement: Julia Moreau | 2026-11-12 | 29 | Completed |  | Vendor ID FV-20931 issued | Tax forms and bank details sent the same day Julia asked. |
| Agree the contract | Send the order form and master subscription agreement | Deal Desk: Owen Park | Procurement: Julia Moreau | 2026-11-13 | 28 | Completed |  | Contract package sent to Julia and Ben | Sent on our paper. Ben agreed after seeing the DPA already covers their EU subsidiaries. |
| Agree the contract | Return redlines on the master subscription agreement | Seller Legal: Hannah Brooks | Legal: Ben Adeyemi | 2026-11-23 | 18 | In progress | Send the order form and master subscription agreement | Redlined agreement received | Ben expects to push on the liability cap and the data processing addendum. Hannah has pre-approved fallback language for both. |
| Agree the contract | Agree final pricing and payment terms | Account Executive: Maya Lindqvist | Procurement: Julia Moreau | 2026-12-01 | 10 | Not started | Return redlines on the master subscription agreement | Final order form with no open comments | Julia asked for net 60. We can offer net 45 with annual upfront billing. |
| Sign | Route the contract to the CFO for signature in DocuSign | Deal Desk: Owen Park | Procurement: Julia Moreau | 2026-12-08 | 3 | Not started | Agree final pricing and payment terms | DocuSign envelope sent | Rebecca signs on Tuesdays and Fridays. Envelope must be in her queue by Tuesday 8 December. |
| Sign | Sign the order form | Sales Leader: Grace Whitfield | Economic Buyer: Rebecca Shaw | 2026-12-11 | 0 | Not started | Route the contract to the CFO for signature in DocuSign | Countersigned order form | Grace countersigns the same day. |
| Get ready to start | Name the Halvorsen project lead and system admins | Implementation Lead: Lena Hoffmann | Champion: Daniel Okafor | 2026-12-04 | 7 | Not started |  | Project team listed in the Deal Room | Daniel leads, with Aisha and one admin from Chris's team. |
| Get ready to start | Book the kickoff for the week of 14 December | Implementation Lead: Lena Hoffmann | Champion: Daniel Okafor | 2026-12-11 | 0 | Not started | Name the Halvorsen project lead and system admins | Kickoff invite accepted by the project team | Target: first regions live by 22 January, six days before the board meeting. |