## Cover
Onboarding handoff plan
Use it when the contract is signed and you want the buyer to reach first value without repeating everything they told sales.
Deal
Signature date | 2027-01-29
Seller
Buyer
Seller owner
Buyer owner
How to use
1. Enter your signature date above. Every due date on the Plan sheet is counted from it.
2. Change a row's days before signature to move that row alone.
3. Put a name next to every role, so each row has one owner on each side.
4. Send the plan to your buyer before the planning call and ask them to correct the approvers and lead times.
5. Update the status on every call and note the evidence when a row is completed.
Start a live plan in demoshake
Source: demoshake.com/guides/mutual-action-plan-template

## Plan
Milestone | Action Item | Seller owner | Buyer owner | Due date | Days before signature | Status | Dependency | Evidence of completion | Notes
Hand off from sales to delivery | Brief the implementation team on goals, risks and promises made | Account Executive | Champion | 2027-01-29 | 0 | Not started |  | Handoff notes shared with the implementation team | Include the success criteria from the sales plan word for word. Delivery should never have to ask the buyer twice.
Hand off from sales to delivery | Name the project lead, admins and an executive contact | Implementation Lead | Champion | 2027-02-01 | -3 | Not started |  | Project team listed in this plan
Kickoff | Hold the kickoff and confirm the go-live date | Implementation Lead | Champion | 2027-02-05 | -7 | Not started | Name the project lead, admins and an executive contact | Go-live date agreed and written into this plan
Kickoff | Confirm the success criteria with the Executive Sponsor | Customer Success Manager | Executive Sponsor | 2027-02-08 | -10 | Not started | Hold the kickoff and confirm the go-live date | Sponsor approves the criteria for the first value review
Configure and integrate | Set up SSO and invite the admins | Implementation Lead | IT | 2027-02-12 | -14 | Not started | Hold the kickoff and confirm the go-live date | Admins signed in through SSO
Configure and integrate | Connect the systems agreed in the integration plan | Implementation Lead | IT | 2027-02-22 | -24 | Not started | Set up SSO and invite the admins | Integrations live and data syncing
Configure and integrate | Test the setup against the success criteria | Implementation Lead | Technical Evaluator | 2027-02-28 | -30 | Not started | Connect the systems agreed in the integration plan | Acceptance checklist signed off
Train the users | Train the admins to run the product without help | Implementation Lead | IT | 2027-03-02 | -32 | Not started |  | Admins complete the training checklist
Train the users | Run training sessions for every team going live | Customer Success Manager | End Users | 2027-03-10 | -40 | Not started | Train the admins to run the product without help | Attendance list for each session
Go live | Announce the launch to every user from the Executive Sponsor | Customer Success Manager | Executive Sponsor | 2027-03-14 | -44 | Not started | Run training sessions for every team going live | Launch message sent | A note from the sponsor drives adoption more than any training session.
Go live | Go live and retire the old process | Implementation Lead | Champion | 2027-03-15 | -45 | Not started | Test the setup against the success criteria | Old tool or spreadsheet switched off
First value review | Report adoption and usage for the first 30 days | Customer Success Manager | Champion | 2027-04-14 | -75 | Not started | Go live and retire the old process | Adoption report shared
First value review | Review results against the success criteria with the sponsor | Customer Success Manager | Executive Sponsor | 2027-04-29 | -90 | Not started | Report adoption and usage for the first 30 days | Value review notes with next goals
Formulas:
Due date = Cover!$B5-[Days before signature]