# Procurement and legal sub-plan

Use it when the decision is made but the contract still has to pass vendor onboarding, commercial review and legal redlines.

| Deal |  |
| --- | --- |
| Target signature date | 2027-01-29 |
| Seller |  |
| Buyer |  |
| Seller owner |  |
| Buyer owner |  |

## How to use

1. Every due date counts from the target signature date above. The Excel version re-dates the whole plan from one cell.

2. Mark each row Not started, In progress or Completed as the deal moves.

3. Put a name next to every role, so each row has one owner on each side.

4. Send the plan to your buyer before the planning call and ask them to correct the approvers and lead times.

5. Update the status on every call and note the evidence when a row is completed.

Start a live plan in demoshake

Source: demoshake.com/guides/mutual-action-plan-template

## Plan

| Milestone | Action Item | Seller owner | Buyer owner | Due date | Days before signature | Status | Dependency | Evidence of completion | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vendor onboarding | Confirm every procurement step and how long each one takes | Account Executive | Procurement | 2026-12-20 | 40 | Not started |  | Procurement steps listed in this plan with dates |  |
| Vendor onboarding | Send tax forms, bank details and insurance certificates | Deal Desk | Procurement | 2026-12-24 | 36 | Not started | Confirm every procurement step and how long each one takes | Vendor forms submitted |  |
| Vendor onboarding | Issue a vendor ID and purchase requisition | Deal Desk | Procurement | 2026-12-30 | 30 | Not started | Send tax forms, bank details and insurance certificates | Vendor ID and requisition number |  |
| Commercial terms | Send the order form with pricing, term and payment schedule | Account Executive | Procurement | 2026-12-26 | 34 | Not started |  | Order form received |  |
| Commercial terms | Return commercial questions and requested changes | Deal Desk | Procurement | 2027-01-03 | 26 | Not started | Send the order form with pricing, term and payment schedule | Change requests listed in one reply |  |
| Commercial terms | Agree final pricing and payment terms | Account Executive | Finance | 2027-01-14 | 15 | Not started | Return commercial questions and requested changes | Final order form approved by Finance |  |
| Legal review | Agree whose paper the contract is written on | Seller Legal | Legal | 2026-12-22 | 38 | Not started |  | Contract template agreed | Buyer paper adds weeks. If they insist, ask for it now, not after the business case. |
| Legal review | Send the master agreement and data processing addendum | Seller Legal | Legal | 2026-12-25 | 35 | Not started | Agree whose paper the contract is written on | Agreement in the Legal queue |  |
| Legal review | Return redlines on the agreement | Seller Legal | Legal | 2027-01-05 | 24 | Not started | Send the master agreement and data processing addendum | Redlined agreement received |  |
| Legal review | Hold a call between both legal teams on the open clauses | Seller Legal | Legal | 2027-01-11 | 18 | Not started | Return redlines on the agreement | Open clauses down to a short list | Liability caps, indemnity and data residency are the usual last three. Have fallback language approved before the call. |
| Legal review | Approve the final contract language | Seller Legal | Legal | 2027-01-19 | 10 | Not started | Hold a call between both legal teams on the open clauses | Clean agreement approved by both legal teams |  |
| Approvals and signature | Collect the internal approvals the signer needs | Account Executive | Procurement | 2027-01-23 | 6 | Not started | Approve the final contract language | Approval chain complete |  |
| Approvals and signature | Route the contract to the authorized signer | Deal Desk | Procurement | 2027-01-26 | 3 | Not started | Collect the internal approvals the signer needs | Signature request sent |  |
| Approvals and signature | Sign the contract and issue the purchase order | Sales Leader | Economic Buyer | 2027-01-29 | 0 | Not started | Route the contract to the authorized signer | Countersigned contract and PO number |  |