## Cover
Procurement and legal sub-plan
Use it when the decision is made but the contract still has to pass vendor onboarding, commercial review and legal redlines.
Deal
Target signature date | 2027-01-29
Seller
Buyer
Seller owner
Buyer owner
How to use
1. Enter your target signature date above. Every due date on the Plan sheet is counted from it.
2. Change a row's days before signature to move that row alone.
3. Put a name next to every role, so each row has one owner on each side.
4. Send the plan to your buyer before the planning call and ask them to correct the approvers and lead times.
5. Update the status on every call and note the evidence when a row is completed.
Start a live plan in demoshake
Source: demoshake.com/guides/mutual-action-plan-template

## Plan
Milestone | Action Item | Seller owner | Buyer owner | Due date | Days before signature | Status | Dependency | Evidence of completion | Notes
Vendor onboarding | Confirm every procurement step and how long each one takes | Account Executive | Procurement | 2026-12-20 | 40 | Not started |  | Procurement steps listed in this plan with dates
Vendor onboarding | Send tax forms, bank details and insurance certificates | Deal Desk | Procurement | 2026-12-24 | 36 | Not started | Confirm every procurement step and how long each one takes | Vendor forms submitted
Vendor onboarding | Issue a vendor ID and purchase requisition | Deal Desk | Procurement | 2026-12-30 | 30 | Not started | Send tax forms, bank details and insurance certificates | Vendor ID and requisition number
Commercial terms | Send the order form with pricing, term and payment schedule | Account Executive | Procurement | 2026-12-26 | 34 | Not started |  | Order form received
Commercial terms | Return commercial questions and requested changes | Deal Desk | Procurement | 2027-01-03 | 26 | Not started | Send the order form with pricing, term and payment schedule | Change requests listed in one reply
Commercial terms | Agree final pricing and payment terms | Account Executive | Finance | 2027-01-14 | 15 | Not started | Return commercial questions and requested changes | Final order form approved by Finance
Legal review | Agree whose paper the contract is written on | Seller Legal | Legal | 2026-12-22 | 38 | Not started |  | Contract template agreed | Buyer paper adds weeks. If they insist, ask for it now, not after the business case.
Legal review | Send the master agreement and data processing addendum | Seller Legal | Legal | 2026-12-25 | 35 | Not started | Agree whose paper the contract is written on | Agreement in the Legal queue
Legal review | Return redlines on the agreement | Seller Legal | Legal | 2027-01-05 | 24 | Not started | Send the master agreement and data processing addendum | Redlined agreement received
Legal review | Hold a call between both legal teams on the open clauses | Seller Legal | Legal | 2027-01-11 | 18 | Not started | Return redlines on the agreement | Open clauses down to a short list | Liability caps, indemnity and data residency are the usual last three. Have fallback language approved before the call.
Legal review | Approve the final contract language | Seller Legal | Legal | 2027-01-19 | 10 | Not started | Hold a call between both legal teams on the open clauses | Clean agreement approved by both legal teams
Approvals and signature | Collect the internal approvals the signer needs | Account Executive | Procurement | 2027-01-23 | 6 | Not started | Approve the final contract language | Approval chain complete
Approvals and signature | Route the contract to the authorized signer | Deal Desk | Procurement | 2027-01-26 | 3 | Not started | Collect the internal approvals the signer needs | Signature request sent
Approvals and signature | Sign the contract and issue the purchase order | Sales Leader | Economic Buyer | 2027-01-29 | 0 | Not started | Route the contract to the authorized signer | Countersigned contract and PO number
Formulas:
Due date = Cover!$B5-[Days before signature]