## Cover
Renewal and expansion plan
Use it when a renewal is four months out and you want it signed early, with any expansion decided on proven results.
Deal
Renewal date | 2027-01-29
Seller
Buyer
Seller owner
Buyer owner
How to use
1. Enter your renewal date above. Every due date on the Plan sheet is counted from it.
2. Change a row's days before signature to move that row alone.
3. Put a name next to every role, so each row has one owner on each side.
4. Send the plan to your buyer before the planning call and ask them to correct the approvers and lead times.
5. Update the status on every call and note the evidence when a row is completed.
Start a live plan in demoshake
Source: demoshake.com/guides/mutual-action-plan-template

## Plan
Milestone | Action Item | Seller owner | Buyer owner | Due date | Days before signature | Status | Dependency | Evidence of completion | Notes
Prove the value delivered | Compile results against the original success criteria | Customer Success Manager | Champion | 2026-10-01 | 120 | Not started |  | Value report with numbers per criterion
Prove the value delivered | Confirm the results match what the team sees | Customer Success Manager | Champion | 2026-10-11 | 110 | Not started | Compile results against the original success criteria | Champion signs off the value report
Prove the value delivered | Hold an executive business review with the sponsor | Account Executive | Executive Sponsor | 2026-10-21 | 100 | Not started | Confirm the results match what the team sees | Review held and priorities for next year recorded
Plan the expansion | List the teams or use cases that should come on next | Account Executive | Champion | 2026-10-26 | 95 | Not started | Hold an executive business review with the sponsor | Expansion list with a named owner per team
Plan the expansion | Run a short trial with the next team | Sales Engineer | End Users | 2026-11-15 | 75 | Not started | List the teams or use cases that should come on next | Trial results shared
Renewal business case | Draft the renewal and expansion proposal | Account Executive | Champion | 2026-11-25 | 65 | Not started | Run a short trial with the next team | Proposal with seats, price and term
Renewal business case | Confirm next year's budget covers the renewal and expansion | Account Executive | Economic Buyer | 2026-12-05 | 55 | Not started | Draft the renewal and expansion proposal | Budget approved for the new amount
Commercial and procurement | Review the renewal terms and any changes to the agreement | Deal Desk | Procurement | 2026-12-20 | 40 | Not started | Confirm next year's budget covers the renewal and expansion | Comments returned on the renewal order form
Commercial and procurement | Refresh the annual security review if the policy needs it | Seller Security | Security | 2026-12-25 | 35 | Not started |  | Security review refreshed or waived in writing
Commercial and procurement | Agree final renewal pricing and term | Account Executive | Procurement | 2027-01-09 | 20 | Not started | Review the renewal terms and any changes to the agreement | Final renewal order form
Sign the renewal | Sign the renewal before the current term ends | Account Executive | Economic Buyer | 2027-01-29 | 0 | Not started | Agree final renewal pricing and term | Countersigned renewal
Sign the renewal | Open a new onboarding plan for the expansion teams | Customer Success Manager | Champion | 2027-01-29 | 0 | Not started | List the teams or use cases that should come on next | Onboarding plan shared with the new teams
Formulas:
Due date = Cover!$B5-[Days before signature]