# Security review sub-plan

Use it when the buyer's security team runs a formal vendor risk review and you need it finished before legal signs off.

| Deal |  |
| --- | --- |
| Target signature date | 2027-01-29 |
| Seller |  |
| Buyer |  |
| Seller owner |  |
| Buyer owner |  |

## How to use

1. Every due date counts from the target signature date above. The Excel version re-dates the whole plan from one cell.

2. Mark each row Not started, In progress or Completed as the deal moves.

3. Put a name next to every role, so each row has one owner on each side.

4. Send the plan to your buyer before the planning call and ask them to correct the approvers and lead times.

5. Update the status on every call and note the evidence when a row is completed.

Start a live plan in demoshake

Source: demoshake.com/guides/mutual-action-plan-template

## Plan

| Milestone | Action Item | Seller owner | Buyer owner | Due date | Days before signature | Status | Dependency | Evidence of completion | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Scope the security review | Submit the seller to the vendor risk intake | Account Executive | Champion | 2026-12-10 | 50 | Not started |  | Intake ticket number | The Champion usually has to file this. Ask on the first call, not after the pilot. |
| Scope the security review | Confirm the risk tier and the documents the review needs | Seller Security | Security | 2026-12-14 | 46 | Not started | Submit the seller to the vendor risk intake | Risk tier and document list in writing |  |
| Scope the security review | Describe exactly what data the product will store and process | Sales Engineer | Security | 2026-12-16 | 44 | Not started | Submit the seller to the vendor risk intake | Data flow summary shared |  |
| Share security evidence | Sign an NDA so restricted reports can be shared | Seller Legal | Legal | 2026-12-17 | 43 | Not started |  | Signed NDA |  |
| Share security evidence | Send the SOC 2 Type II report, pen test summary and policies | Seller Security | Security | 2026-12-20 | 40 | Not started | Sign an NDA so restricted reports can be shared | Reports delivered |  |
| Share security evidence | Complete the security questionnaire | Seller Security | Security | 2026-12-26 | 34 | Not started | Confirm the risk tier and the documents the review needs | Completed questionnaire returned | Reuse answers from a trust center or a recent questionnaire. Aim for under a week. |
| Resolve findings | Send the list of findings and follow-up questions | Seller Security | Security | 2027-01-01 | 28 | Not started | Complete the security questionnaire | Findings log shared |  |
| Resolve findings | Hold a call between both security teams to close open questions | Seller Security | Security | 2027-01-05 | 24 | Not started | Send the list of findings and follow-up questions | Call notes with an owner per finding |  |
| Resolve findings | Confirm SSO, user provisioning and network requirements | Sales Engineer | IT | 2027-01-07 | 22 | Not started |  | IT requirements confirmed |  |
| Resolve findings | Agree a fix or a contract commitment for every finding | Seller Security | Security | 2027-01-11 | 18 | Not started | Hold a call between both security teams to close open questions | Every finding marked accepted, fixed or committed |  |
| Security decision | Sign off the vendor risk review | Seller Security | Security | 2027-01-15 | 14 | Not started | Agree a fix or a contract commitment for every finding | Signed risk approval |  |
| Security decision | Pass the security commitments to Legal for the contract | Seller Legal | Legal | 2027-01-17 | 12 | Not started | Sign off the vendor risk review | Security terms included in the draft agreement |  |