## Cover
Security review sub-plan
Use it when the buyer's security team runs a formal vendor risk review and you need it finished before legal signs off.
Deal
Target signature date | 2027-01-29
Seller
Buyer
Seller owner
Buyer owner
How to use
1. Enter your target signature date above. Every due date on the Plan sheet is counted from it.
2. Change a row's days before signature to move that row alone.
3. Put a name next to every role, so each row has one owner on each side.
4. Send the plan to your buyer before the planning call and ask them to correct the approvers and lead times.
5. Update the status on every call and note the evidence when a row is completed.
Start a live plan in demoshake
Source: demoshake.com/guides/mutual-action-plan-template

## Plan
Milestone | Action Item | Seller owner | Buyer owner | Due date | Days before signature | Status | Dependency | Evidence of completion | Notes
Scope the security review | Submit the seller to the vendor risk intake | Account Executive | Champion | 2026-12-10 | 50 | Not started |  | Intake ticket number | The Champion usually has to file this. Ask on the first call, not after the pilot.
Scope the security review | Confirm the risk tier and the documents the review needs | Seller Security | Security | 2026-12-14 | 46 | Not started | Submit the seller to the vendor risk intake | Risk tier and document list in writing
Scope the security review | Describe exactly what data the product will store and process | Sales Engineer | Security | 2026-12-16 | 44 | Not started | Submit the seller to the vendor risk intake | Data flow summary shared
Share security evidence | Sign an NDA so restricted reports can be shared | Seller Legal | Legal | 2026-12-17 | 43 | Not started |  | Signed NDA
Share security evidence | Send the SOC 2 Type II report, pen test summary and policies | Seller Security | Security | 2026-12-20 | 40 | Not started | Sign an NDA so restricted reports can be shared | Reports delivered
Share security evidence | Complete the security questionnaire | Seller Security | Security | 2026-12-26 | 34 | Not started | Confirm the risk tier and the documents the review needs | Completed questionnaire returned | Reuse answers from a trust center or a recent questionnaire. Aim for under a week.
Resolve findings | Send the list of findings and follow-up questions | Seller Security | Security | 2027-01-01 | 28 | Not started | Complete the security questionnaire | Findings log shared
Resolve findings | Hold a call between both security teams to close open questions | Seller Security | Security | 2027-01-05 | 24 | Not started | Send the list of findings and follow-up questions | Call notes with an owner per finding
Resolve findings | Confirm SSO, user provisioning and network requirements | Sales Engineer | IT | 2027-01-07 | 22 | Not started |  | IT requirements confirmed
Resolve findings | Agree a fix or a contract commitment for every finding | Seller Security | Security | 2027-01-11 | 18 | Not started | Hold a call between both security teams to close open questions | Every finding marked accepted, fixed or committed
Security decision | Sign off the vendor risk review | Seller Security | Security | 2027-01-15 | 14 | Not started | Agree a fix or a contract commitment for every finding | Signed risk approval
Security decision | Pass the security commitments to Legal for the contract | Seller Legal | Legal | 2027-01-17 | 12 | Not started | Sign off the vendor risk review | Security terms included in the draft agreement
Formulas:
Due date = Cover!$B5-[Days before signature]