## Cover
SMB mutual action plan
Use it when one or two people decide, there is no formal procurement, and the deal should close in two to four weeks.
Deal
Target signature date | 2027-01-29
Seller
Buyer
Seller owner
Buyer owner
How to use
1. Enter your target signature date above. Every due date on the Plan sheet is counted from it.
2. Change a row's days before signature to move that row alone.
3. Put a name next to every role, so each row has one owner on each side.
4. Send the plan to your buyer before the planning call and ask them to correct the approvers and lead times.
5. Update the status on every call and note the evidence when a row is completed.
Start a live plan in demoshake
Source: demoshake.com/guides/mutual-action-plan-template

## Plan
Milestone | Action Item | Seller owner | Buyer owner | Due date | Days before signature | Status | Dependency | Evidence of completion | Notes
Agree on the goal | Agree on the one problem to solve and a signature date | Account Executive | Champion | 2027-01-08 | 21 | Not started |  | Goal and date written at the top of this plan
Agree on the goal | Confirm who signs and whether anyone else needs to say yes | Account Executive | Champion | 2027-01-09 | 20 | Not started |  | Signer named in this plan
Try it on real work | Set up a trial workspace with the buyer's own data | Sales Engineer | Champion | 2027-01-11 | 18 | Not started | Agree on the one problem to solve and a signature date | Trial workspace live
Try it on real work | Use the product on one live piece of work | Sales Engineer | End Users | 2027-01-17 | 12 | Not started | Set up a trial workspace with the buyer's own data | One real task completed in the trial
Try it on real work | Review what worked and what is missing on a 20-minute call | Account Executive | Champion | 2027-01-19 | 10 | Not started | Use the product on one live piece of work | Open questions listed and answered
Confirm price and budget | Send a quote with the plan, seats and start date | Account Executive | Economic Buyer | 2027-01-21 | 8 | Not started |  | Quote received
Confirm price and budget | Confirm the spend is approved | Account Executive | Economic Buyer | 2027-01-24 | 5 | Not started | Send a quote with the plan, seats and start date | Approval by email or chat
Approve and sign | Review the standard terms and raise any blockers | Account Executive | Economic Buyer | 2027-01-26 | 3 | Not started |  | No open questions on the terms | Most small deals sign on standard terms. If a blocker appears here, add a Legal row with a date.
Approve and sign | Sign the order form or check out online | Account Executive | Economic Buyer | 2027-01-29 | 0 | Not started | Confirm the spend is approved | Signed order or receipt
Get started | Invite the first users | Customer Success Manager | Champion | 2027-01-29 | 0 | Not started |  | First users signed in
Get started | Book a 30-minute onboarding call for the first week | Customer Success Manager | Champion | 2027-01-29 | 0 | Not started |  | Onboarding call on the calendar
Formulas:
Due date = Cover!$B5-[Days before signature]